## HIOReportOutput
Region | NSP | Start | Finish | Network Asset | Impact | Recall | Status | Status and Market Notice | Project Work? | Unplanned? | DNSP Aware? | Generator Aware? | Inter-Regional | Impact Region, Reason and Duration | Vs Old | Duration
VIC | AusNet | 2024-08-19 06:30 | 2024-08-19 18:00 | Hazelwood - Rowville 500 kV Line | <<This outage has been WITHDRAWN!>> This is a high impact outage only if the Forecast Operational Demand in Victoria region is greater than 7,000 MW A credible contingency event during this planned outage could: • Cause a large reduction in generation in Victoria • Restrict power transfer across the Victoria - South Australia interconnector (Heywood interconnector). | Day: 2 hrs-Night: NA | Withdrawn | Withdrawn | [5 empty] | VIC Maintenance 11.5 Hours | #REF! | 11.5 Hours
VIC | AusNet | 2024-08-20 06:00 | 2024-08-20 19:30 | Kerang-Wemen 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 6.5 hrs-Night: NA | Planned - STLTP | Planned - STLTP | T |  | T | T | T | VIC Maintenance 13.5 Hours | #REF! | 13.5 Hours
VIC | AusNet | 2024-08-21 06:00 | 2024-08-21 18:00 | Kerang-Wemen 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 6.5 hrs-Night: NA | Planned - MTLTP | Planned - MTLTP | T |  | T | T | T | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2024-08-22 06:00 | 2024-08-22 18:00 | Kerang-Wemen 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 6.5 hrs-Night: NA | Planned - MTLTP | Planned - MTLTP | T |  | T | T | T | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2024-08-22 07:00 | 2024-08-22 18:00 | Haunted Gully - Tarrone 500 Kv line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 2 hrs-Night: NA | Planned - MTLTP | Planned - MTLTP |  |  |  | T | T | VIC / SA Maintenance 11 Hours | #REF! | 11 Hours
VIC | AusNet | 2024-08-23 07:00 | 2024-08-23 18:00 | Haunted Gully - Tarrone 500 Kv line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 2 hrs-Night: NA | Planned - MTLTP | Planned - MTLTP |  |  |  | T | T | VIC / SA Maintenance 11 Hours | #REF! | 11 Hours
VIC | AusNet | 2024-08-25 06:30 | 2024-08-25 17:30 | Red Cliffs No.2 220 kV Bus | This bus outage offloads Red Cliffs - Kiamal 220kV line, and Red Cliffs capacitor banks will be unavailable for automatic switching. A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 2 hrs-Night: NA | Planned - MTLTP | Planned - MTLTP | T |  | T | T | T | VIC Maintenance 11 Hours | #REF! | 11 Hours
VIC | AusNet | 2024-08-26 06:30 | 2024-08-26 17:30 | Red Cliffs No.2 220 kV Bus | This bus outage offloads Red Cliffs - Kiamal 220kV line, and Red Cliffs capacitor banks will be unavailable for automatic switching. A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 2 hrs-Night: NA | Planned - MTLTP | Planned - MTLTP | T |  | T | T | T | VIC Maintenance 11 Hours | #REF! | 11 Hours
VIC | AusNet | 2024-08-26 07:00 | 2024-08-26 16:30 | Rowville - South Morang 500 kV Line | This is a high impact outage only if the Forecast Operational Demand in Victoria region is greater than 7,000 MW A credible contingency event during this planned outage could: • Cause a large reduction in generation in Victoria • Restrict power transfer across the Victoria - South Australia interconnector (Heywood interconnector). | Day: 2 hrs-Night: NA | Planned - MTLTP | Planned - MTLTP | [5 empty] | VIC Maintenance 9.5 Hours | #REF! | 9.5 Hours
VIC | AusNet | 2024-08-27 06:30 | 2024-08-27 17:30 | Red Cliffs No.2 220 kV Bus | This bus outage offloads Red Cliffs - Kiamal 220kV line, and Red Cliffs capacitor banks will be unavailable for automatic switching. A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 2 hrs-Night: NA | Planned - MTLTP | Planned - MTLTP | T |  | T | T | T | VIC Maintenance 11 Hours | #REF! | 11 Hours
VIC | AusNet | 2024-08-29 06:00 | 2024-08-29 18:00 | Kerang-Wemen 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 3 hrs-Night: NA | Planned - MTLTP | Planned - MTLTP | T |  | T | T | T | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2024-08-29 06:30 | 2024-08-29 17:00 | South Morang - Sydenham No.1 500 kV Line | This is a high impact outage only if the Forecast Operational Demand in Victoria region is greater than 7,000 MW A credible contingency event during this planned outage could: • Cause a large reduction in generation in Victoria • Restrict power transfer across the Victoria - South Australia interconnector (Heywood interconnector). | Day: 2 hrs-Night: NA | Planned - MTLTP | Planned - MTLTP | [5 empty] | VIC Maintenance 10.5 Hours | #REF! | 10.5 Hours
NSW | Transgrid | 2024-08-30 07:00 | 2024-09-01 17:00 | Buronga - Red Cliffs (X1) 220 kV line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 12 hrs-Night: 12 hrs | Planned - MTLTP | Planned - MTLTP |  |  | T | T | T | NSW / VIC Commissioning 2.4 Days | #REF! | 2.4 Days
VIC | AusNet | 2024-09-04 06:30 | 2024-09-04 16:30 | Hazelwood - Loy Yang Power Station No.1 500 kV Line | A credible contingency event during this planned outage could cause: • A large reduction in generation in Victoria • Load shedding in Victoria | Day: 2 hrs-Night: NA | Planned - MTLTP | Planned - MTLTP | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
NSW | Transgrid | 2024-09-04 07:00 | 2024-09-05 17:00 | Liddell to Muswellbrook (83) 330 kV Line | <<NEW since the last notification>> A credible contingency event during this planned outage could cause: • Synchronous separation of the Queensland region from the rest of the NEM | Day: 2 hrs-Night: 4 hrs | Planned - MTLTP | Planned - MTLTP |  |  | T | T | T | NSW / QLD Maintenance 1.4 Days | #REF! | 1.4 Days
VIC | AusNet | 2024-09-05 06:30 | 2024-09-05 18:30 | Hazelwood - Loy Yang Power Station No.2 500 kV Line | A credible contingency event during this planned outage could cause: • A large reduction in generation in Victoria • Load shedding in Victoria | Day: 2 hrs-Night: NA | Planned - MTLTP | Planned - MTLTP | [5 empty] | VIC Maintenance 12 Hours | #REF! | 12 Hours
QLD | Powerlink | 2024-09-05 07:30 | 2024-09-05 17:00 | Nebo - Strathmore (8845) 275 kV Line | This is a high impact outage because the recall time is greater than 30 minutes. A credible contingency event during this planned outage may require market intervention through issuing of directions. | Day: 4 hrs-Night: NA | Planned - MTLTP | Planned - MTLTP | [5 empty] | QLD Maintenance 9.5 Hours | #REF! | 9.5 Hours
NSW | Transgrid | 2024-09-09 05:30 | 2024-09-09 22:00 | Balranald - Darlington Point (X5) 220 kV Line | During this planned outage power transfer will be restricted • Between Victoria and New South Wales. • Between South Australia and Victoria on Murraylink A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 12 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT |  |  |  | T | T | NSW / VIC Commissioning 16.5 Hours | #REF! | 16.5 Hours
VIC | AusNet | 2024-09-11 06:30 | 2024-09-11 17:00 | Hazelwood - Loy Yang Power Station No.3 500 kV Line | A credible contingency event during this planned outage could cause: • A large reduction in generation in Victoria • Load shedding in Victoria | Day: 2 hrs-Night: NA | Planned - MTLTP | Planned - MTLTP | [5 empty] | VIC Maintenance 10.5 Hours | #REF! | 10.5 Hours
QLD | Powerlink | 2024-09-11 08:00 | 2024-09-11 17:00 | Stanwell - Broadsound (856) 275 kV Line | This is a high impact outage because the recall time is greater than 30 minutes. A credible contingency event during this planned outage may result in shedding Far North QLD load and Lilyvale local load. Following a credible contingency market intervention through issuing of directions may be required. If market intervention is unsuccessful all of North QLD load would be in a credible risk | Day: 3 hrs-Night: NA | Planned - MTLTP | Planned - MTLTP |  |  |  | T |  | QLD Maintenance 9 Hours | #REF! | 9 Hours
VIC | AusNet | 2024-09-13 06:00 | 2024-09-13 18:00 | Red Cliffs No.1 220 kV Bus | <<NEW since the last notification>> This bus outage offloads Red Cliffs - Wemen 220kV line, and Red Cliffs capacitor banks will be unavailable for automatic switching. A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | T |  | T | T | T | VIC Commissioning 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2024-09-16 06:00 | 2024-09-16 18:00 | Red Cliffs No.2 220 kV Bus | This bus outage offloads Red Cliffs - Kiamal 220kV line, and Red Cliffs capacitor banks will be unavailable for automatic switching. A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: NA-Night: NA | Planned - MTLTP | Planned - MTLTP | T |  | T | T | T | VIC Maintenance 12 Hours | #REF! | 12 Hours
QLD | Powerlink | 2024-09-16 07:00 | 2024-09-16 07:59 | Haughton River - Ross (8911) 275 kV Line | <<NEW since the last notification>> This is a high impact outage because the recall time is greater than 30 minutes. A credible contingency event during this planned outage may require market intervention through issuing of directions. | Day: 30 mins-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | QLD Commissioning 59 Minutes | #REF! | 59 Minutes
QLD | Powerlink | 2024-09-16 08:00 | 2024-09-20 16:00 | Strathmore - Ross (8857) 275 kV Line | <<NEW since the last notification>> This is a high impact outage because the recall time is greater than 30 minutes. A credible contingency event during this planned outage may require market intervention through issuing of directions. | Day: 8 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT |  |  | T | T |  | Commissioning 4.3 Days | #REF! | 4.3 Days
VIC | AusNet | 2024-09-17 06:00 | 2024-09-17 18:00 | Red Cliffs No.2 220 kV Bus | This bus outage offloads Red Cliffs - Kiamal 220kV line, and Red Cliffs capacitor banks will be unavailable for automatic switching. A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: NA-Night: NA | Planned - MTLTP | Planned - MTLTP | T |  | T | T | T | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2024-09-18 06:00 | 2024-09-18 18:00 | Red Cliffs No.2 220 kV Bus | <<NEW since the last notification>> This bus outage offloads Red Cliffs - Kiamal 220kV line, and Red Cliffs capacitor banks will be unavailable for automatic switching. A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: NA-Night: NA | Planned - MTLTP | Planned - MTLTP | T |  | T | T | T | VIC Maintenance 12 Hours | #REF! | 12 Hours
NSW | Transgrid | 2024-09-20 06:00 | 2024-09-28 18:00 | Jindera - Wagga (62) 330 kV Line | This outage offloads the Buronga to Darlington Point X5 220 kV line and restricts power transfer • Between Victoria and New South Wales. • Between South Australia and Victoria on Murraylink A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 4 hrs-Night: 6 hrs | Planned - MTLTP | Planned - MTLTP | [5 empty] | NSW/ VIC Maintenance 8.5 Days | #REF! | 8.5 Days
QLD | Powerlink | 2024-09-20 16:01 | 2024-09-20 17:00 | Haughton River - Ross (8911) 275 kV Line | <<NEW since the last notification>> This is a high impact outage because the recall time is greater than 30 minutes. A credible contingency event during this planned outage may require market intervention through issuing of directions. | Day: 30 mins-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | QLD Commissioning 59 Minutes | #REF! | 59 Minutes
VIC | AusNet | 2024-09-26 07:00 | 2024-09-26 17:30 | Hazelwood - South Morang No.2 500 kV Line | This is a high impact outage only if the Forecast Operational Demand in Victoria region is greater than 7,000 MW A credible contingency event during this planned outage could: • Cause a large reduction in generation in Victoria • Restrict power transfer across the Victoria - South Australia interconnector (Heywood interconnector). | Day: 2 hrs-Night: NA | Planned - MTLTP | Planned - MTLTP | [5 empty] | VIC Maintenance 10.5 Hours | #REF! | 10.5 Hours
NSW | Transgrid | 2024-09-30 05:30 | 2024-09-30 22:00 | Jindera - Wagga (62) 330 kV Line | This outage offloads the Buronga to Darlington Point X5 220 kV line and restricts power transfer • Between Victoria and New South Wales. • Between South Australia and Victoria on Murraylink A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 12 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | NSW/ VIC Commissioning 16.5 Hours | #REF! | 16.5 Hours
VIC | AusNet | 2024-10-01 06:00 | 2024-10-11 20:30 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 72 hrs-Night: 84 hrs | Planned - MTLTP | Planned - MTLTP | [5 empty] | VIC Maintenance 10.6 Days | #REF! | 10.6 Days
VIC | AusNet | 2024-10-07 06:00 | 2024-10-07 16:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2024-10-12 06:00 | 2024-10-12 16:00 | Ararat - Crowlands 220kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - RESUBMIT | Planned - RESUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2024-10-22 06:00 | 2024-11-01 20:30 | Moorabool–Sydenham No.1 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 72 hrs-Night: 84 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10.6 Days | #REF! | 10.6 Days
TAS | TasNetworks | 2024-10-28 05:00 | 2024-11-01 20:00 | George Town - George Town Converter Station 220 kV Line | Tasmania will be separated from the NEM | Day: 4 hrs-Night: 6 hrs | Planned - SUBMIT | Planned - SUBMIT |  |  |  | T |  | TAS Maintenance 4.6 Days | #REF! | 4.6 Days
VIC | AusNet | 2024-10-31 05:00 | 2024-10-31 17:00 | Kerang-Wemen 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2024-11-01 06:00 | 2024-11-01 16:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2024-11-04 06:00 | 2024-11-04 16:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
TAS | TasNetworks | 2024-11-05 11:00 | 2024-11-05 13:00 | Gordon - Chapel St No.1 220 kV Line | A credible contingency event during this planned outage could cause a large reduction in generation in Tasmania. | Day: 1 hr-Night: NA | Planned - RESUBMIT | Planned - RESUBMIT |  |  |  | T |  | TAS Maintenance 2 Hours | #REF! | 2 Hours
VIC | AusNet | 2024-11-09 06:00 | 2024-11-09 16:00 | Kiamal SF - MurraWarra 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2024-11-11 06:00 | 2024-11-11 16:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2024-11-11 06:00 | 2024-11-11 16:00 | Haunted Gully - Tarrone 500 Kv line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC / SA Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2024-11-12 06:00 | 2024-11-12 16:00 | Ararat - Crowlands 220kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2024-11-14 06:00 | 2024-11-14 16:00 | Moorabool - Mortlake 500 kV Line | <<This outage has been WITHDRAWN!>> A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 2 hrs-Night: NA | Withdrawn | Withdrawn | [5 empty] | VIC / SA Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2024-11-18 06:00 | 2024-11-18 16:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2024-11-21 06:00 | 2024-11-22 16:00 | Haunted Gully - Tarrone 500 Kv line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 1 hr-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC / SA Maintenance 1.4 Days | #REF! | 1.4 Days
VIC | AusNet | 2024-11-23 06:00 | 2024-11-24 16:00 | Haunted Gully - Tarrone 500 Kv line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 1 hr-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC / SA Maintenance 1.4 Days | #REF! | 1.4 Days
VIC | AusNet | 2024-11-25 06:00 | 2024-11-25 16:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
QLD | Powerlink | 2024-11-25 08:00 | 2024-11-29 17:00 | Nebo - Strathmore (822) 275 kV Line | This is a high impact outage because the recall time is greater than 30 minutes. A credible contingency event during this planned outage may require market intervention through issuing of directions. | Day: 48 hrs-Night: 48 hrs | Planned - SUBMIT | Planned - SUBMIT |  |  | T |  |  | QLD Maintenance 4.4 Days | #REF! | 4.4 Days
VIC | AusNet | 2024-11-26 05:00 | 2024-11-26 17:00 | Red Cliffs-Wemen 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: NA-Night: NA | Planned - SUBMIT | Planned - SUBMIT | T |  |  |  |  | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2024-11-28 05:00 | 2024-11-28 17:00 | Red Cliffs-Wemen 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: NA-Night: NA | Planned - SUBMIT | Planned - SUBMIT | T |  |  |  |  | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2024-12-02 06:00 | 2024-12-02 16:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2024-12-04 05:00 | 2024-12-04 17:00 | Kerang-Wemen 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 8 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | T |  |  |  |  | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2024-12-06 05:00 | 2024-12-06 17:00 | Kerang-Wemen 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 8 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | T |  |  |  |  | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2024-12-09 06:00 | 2024-12-09 16:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2024-12-09 06:00 | 2024-12-09 16:00 | Kiamal SF - MurraWarra 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
QLD | Powerlink | 2024-12-09 08:00 | 2024-12-11 17:00 | Strathmore - Ross (8857) 275 kV Line | This is a high impact outage because the recall time is greater than 30 minutes. A credible contingency event during this planned outage may require market intervention through issuing of directions. | Day: 6 hrs-Night: 8 hrs | Planned - RESUBMIT | Planned - RESUBMIT |  |  |  | T |  | QLD Commissioning 2.4 Days | #REF! | 2.4 Days
VIC | AusNet | 2024-12-12 06:00 | 2024-12-12 16:00 | Haunted Gully - Tarrone 500 Kv line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | T |  |  |  |  | VIC / SA Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2024-12-13 05:00 | 2024-12-13 17:00 | Kerang-Wemen 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 5 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | T |  |  |  |  | VIC Maintenance 12 Hours | #REF! | 12 Hours
TAS | TasNetworks | 2024-12-18 11:00 | 2024-12-18 13:00 | Gordon - Chapel St No.2 220 kV Line | <<NEW since the last notification>> A credible contingency event during this planned outage could cause a large reduction in generation in Tasmania. | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT |  |  |  | T |  | TAS Commissioning 2 Hours | #REF! | 2 Hours
TAS | TasNetworks | 2024-12-19 13:00 | 2024-12-19 15:30 | Gordon - Chapel St No.2 220 kV Line | A credible contingency event during this planned outage could cause a large reduction in generation in Tasmania. | Day: 1 hr-Night: NA | Planned - RESUBMIT | Planned - RESUBMIT |  |  |  | T |  | TAS Commissioning 2.5 Hours | #REF! | 2.5 Hours
VIC | AusNet | 2024-12-31 05:30 | 2024-12-31 16:00 | Kiamal SF-Red Cliffs 220 kV LINE | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10.5 Hours | #REF! | 10.5 Hours
VIC | AusNet | 2024-12-31 06:00 | 2024-12-31 17:00 | Kiamal SF - MurraWarra 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 11 Hours | #REF! | 11 Hours
VIC | AusNet | 2024-12-31 06:00 | 2024-12-31 16:00 | Red Cliffs-Wemen 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2024-12-31 06:00 | 2024-12-31 16:00 | Red Cliffs-Wemen 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-01-04 06:00 | 2025-01-04 16:00 | Bulgana - Horsham 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-01-04 06:00 | 2025-01-04 16:00 | Crowland - Bulgana 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-01-13 06:00 | 2025-01-13 18:00 | Moorabool–Sydenham No.1 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2025-01-14 06:00 | 2025-01-14 18:00 | Moorabool–Sydenham No.1 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2025-01-20 06:00 | 2025-01-20 21:00 | Moorabool - Mortlake 500 kV Line | <<This outage has been WITHDRAWN!>> A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 2 hrs-Night: NA | Withdrawn | Withdrawn | [5 empty] | VIC / SA Maintenance 15 Hours | #REF! | 15 Hours
VIC | AusNet | 2025-01-20 06:00 | 2025-01-20 16:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-01-22 07:00 | 2025-01-22 17:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - RESUBMIT | Planned - RESUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-01-27 06:00 | 2025-01-27 16:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-02-03 06:00 | 2025-02-03 16:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-02-03 06:00 | 2025-02-03 18:00 | Moorabool–Sydenham No.1 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2025-02-03 07:00 | 2025-02-03 17:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - RESUBMIT | Planned - RESUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-02-04 06:00 | 2025-02-04 16:00 | Bulgana - Horsham 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-02-04 06:00 | 2025-02-04 16:00 | Crowland - Bulgana 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-02-04 06:00 | 2025-02-04 16:00 | Bulgana - Horsham 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-02-10 06:00 | 2025-02-10 16:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-02-11 07:00 | 2025-02-11 17:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-02-17 06:00 | 2025-02-17 16:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-02-17 07:00 | 2025-02-17 17:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-02-21 06:00 | 2025-02-21 18:00 | Moorabool–Sydenham No.1 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2025-02-22 06:00 | 2025-02-22 18:00 | Moorabool–Sydenham No.1 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2025-02-23 06:00 | 2025-02-23 18:00 | Moorabool–Sydenham No.1 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2025-02-24 06:00 | 2025-02-24 16:00 | Moorabool–Sydenham No.1 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-02-25 07:00 | 2025-02-25 17:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-03-01 06:00 | 2025-03-01 16:00 | Moorabool - Mortlake 500 kV Line | <<This outage has been WITHDRAWN!>> A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 2 hrs-Night: NA | Withdrawn | Withdrawn | [5 empty] | VIC / SA Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-03-02 06:00 | 2025-03-02 16:00 | Moorabool - Mortlake 500 kV Line | <<This outage has been WITHDRAWN!>> A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 2 hrs-Night: NA | Withdrawn | Withdrawn | [5 empty] | VIC / SA Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-03-03 05:00 | 2025-03-03 17:00 | Kiamal SF-Red Cliffs 220 kV LINE | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 3 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2025-03-03 06:00 | 2025-03-03 16:00 | Moorabool–Sydenham No.1 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
QLD | Powerlink | 2025-03-03 08:00 | 2025-03-07 17:00 | Nebo - Strathmore (822) 275 kV Line | This is a high impact outage because the recall time is greater than 30 minutes. A credible contingency event during this planned outage may require market intervention through issuing of directions. | Day: 48 hrs-Night: 48 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | QLD Maintenance 4.4 Days | #REF! | 4.4 Days
VIC | AusNet | 2025-03-04 05:00 | 2025-03-04 17:00 | Kiamal SF-Red Cliffs 220 kV LINE | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 3 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2025-03-04 06:00 | 2025-03-04 16:00 | Kiamal SF - MurraWarra 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-03-04 06:00 | 2025-03-04 16:00 | Horsham - MurraWarra 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-03-05 05:00 | 2025-03-05 17:00 | Kiamal SF-Red Cliffs 220 kV LINE | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 3 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2025-03-05 06:00 | 2025-03-05 16:00 | Moorabool–Sydenham No.2 500 kV Line | <<NEW since the last notification>> A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-03-06 05:00 | 2025-03-06 17:00 | Kiamal SF-Red Cliffs 220 kV LINE | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 3 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2025-03-07 05:00 | 2025-03-13 17:00 | Moorabool - Mortlake 500 kV Line | <<This outage has been WITHDRAWN!>> A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 2 hrs-Night: NA | Withdrawn | Withdrawn | [5 empty] | VIC / SA Maintenance 6.5 Days | #REF! | 6.5 Days
VIC | AusNet | 2025-03-07 05:00 | 2025-03-07 17:00 | Kiamal SF-Red Cliffs 220 kV LINE | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 3 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 12 Hours | #REF! | 12 Hours
QLD | Powerlink | 2025-03-07 17:01 | 2025-08-19 07:59 | Nebo - Strathmore (822) 275 kV Line | This is a high impact outage because the recall time is greater than 30 minutes. A credible contingency event during this planned outage may require market intervention through issuing of directions. | Day: 0 mins-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | QLD Maintenance 164.6 Days | #REF! | 164.6 Days
VIC | AusNet | 2025-03-10 06:00 | 2025-03-10 16:00 | Moorabool–Sydenham No.1 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-03-17 06:00 | 2025-03-19 16:00 | Moorabool - Mortlake 500 kV Line | <<This outage has been WITHDRAWN!>> A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 2 hrs-Night: NA | Withdrawn | Withdrawn | [5 empty] | VIC / SA Maintenance 2.4 Days | #REF! | 2.4 Days
VIC | AusNet | 2025-03-18 06:00 | 2025-03-18 17:00 | Moorabool–Sydenham No.1 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 11 Hours | #REF! | 11 Hours
VIC | AusNet | 2025-03-19 06:00 | 2025-03-19 17:00 | Moorabool–Sydenham No.1 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 11 Hours | #REF! | 11 Hours
VIC | AusNet | 2025-03-21 06:00 | 2025-03-21 17:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 11 Hours | #REF! | 11 Hours
VIC | AusNet | 2025-03-22 06:00 | 2025-03-22 17:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 11 Hours | #REF! | 11 Hours
VIC | AusNet | 2025-03-22 06:00 | 2025-03-22 16:00 | Moorabool–Sydenham No.2 500 kV Line | <<NEW since the last notification>> A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-03-23 05:00 | 2025-03-23 17:00 | Kiamal SF-Red Cliffs 220 kV LINE | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 3 hrs-Night: NA | Planned - RESUBMIT | Planned - RESUBMIT | T |  |  |  |  | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2025-03-24 05:00 | 2025-03-24 17:00 | Kiamal SF-Red Cliffs 220 kV LINE | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 3 hrs-Night: NA | Planned - RESUBMIT | Planned - RESUBMIT | T |  |  |  |  | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2025-03-25 05:00 | 2025-03-25 17:00 | Kiamal SF-Red Cliffs 220 kV LINE | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 3 hrs-Night: NA | Planned - RESUBMIT | Planned - RESUBMIT | T |  |  |  |  | VIC Maintenance 12 Hours | #REF! | 12 Hours
QLD | Powerlink | 2025-03-25 08:00 | 2025-03-27 16:00 | Nebo - Strathmore (822) 275 kV Line | This is a high impact outage because the recall time is greater than 30 minutes. A credible contingency event during this planned outage may require market intervention through issuing of directions. | Day: 2 hrs-Night: 4 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | QLD Commissioning 2.3 Days | #REF! | 2.3 Days
VIC | AusNet | 2025-03-26 05:00 | 2025-03-26 17:00 | Kiamal SF-Red Cliffs 220 kV LINE | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 3 hrs-Night: NA | Planned - RESUBMIT | Planned - RESUBMIT | T |  |  |  |  | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2025-03-27 05:00 | 2025-03-27 17:00 | Kiamal SF-Red Cliffs 220 kV LINE | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 2 hrs-Night: NA | Planned - RESUBMIT | Planned - RESUBMIT | T |  |  |  |  | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2025-03-27 06:00 | 2025-03-28 16:00 | Rowville - South Morang 500 kV Line | This is a high impact outage only if the Forecast Operational Demand in Victoria region is greater than 7,000 MW A credible contingency event during this planned outage could: • Cause a large reduction in generation in Victoria • Restrict power transfer across the Victoria - South Australia interconnector (Heywood interconnector). | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 1.4 Days | #REF! | 1.4 Days
VIC | AusNet | 2025-03-28 06:00 | 2025-03-28 18:00 | Kiamal SF-Red Cliffs 220 kV LINE | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 3 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2025-04-02 06:00 | 2025-04-02 16:00 | Haunted Gully - Tarrone 500 Kv line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC / SA Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-04-03 06:00 | 2025-04-03 18:00 | Kiamal SF-Red Cliffs 220 kV LINE | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | T |  |  |  |  | VIC Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2025-04-04 06:00 | 2025-04-04 16:00 | Kiamal SF - MurraWarra 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-04-04 06:00 | 2025-04-04 16:00 | Horsham - MurraWarra 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-04-04 06:00 | 2025-04-04 16:00 | Horsham - MurraWarra 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-04-06 07:00 | 2025-04-08 18:00 | South Morang - Sydenham No.1 500 kV Line | This is a high impact outage only if the Forecast Operational Demand in Victoria region is greater than 7,000 MW A credible contingency event during this planned outage could: • Cause a large reduction in generation in Victoria • Restrict power transfer across the Victoria - South Australia interconnector (Heywood interconnector). | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 2.5 Days | #REF! | 2.5 Days
VIC | AusNet | 2025-04-06 12:00 | 2025-04-06 17:00 | Moorabool - Mortlake 500 kV Line | <<This outage has been WITHDRAWN!>> A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 2 hrs-Night: NA | Withdrawn | Withdrawn | [5 empty] | VIC / SA Maintenance 5 Hours | #REF! | 5 Hours
VIC | AusNet | 2025-04-10 07:00 | 2025-04-15 18:00 | South Morang - Sydenham No.1 500 kV Line | This is a high impact outage only if the Forecast Operational Demand in Victoria region is greater than 7,000 MW A credible contingency event during this planned outage could: • Cause a large reduction in generation in Victoria • Restrict power transfer across the Victoria - South Australia interconnector (Heywood interconnector). | Day: 120 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 5.5 Days | #REF! | 5.5 Days
VIC | AusNet | 2025-04-28 07:00 | 2025-04-30 18:00 | South Morang - Sydenham No.2 500 kV Line | This is a high impact outage only if the Forecast Operational Demand in Victoria region is greater than 7,000 MW A credible contingency event during this planned outage could: • Cause a large reduction in generation in Victoria • Restrict power transfer across the Victoria - South Australia interconnector (Heywood interconnector). | Day: 24 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 2.5 Days | #REF! | 2.5 Days
VIC | TOA | 2025-04-28 07:00 | 2025-04-28 12:00 | Ararat - Waubra 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: NA-Night: NA | Planned - SUBMIT | Planned - SUBMIT | T |  |  |  |  | VIC Maintenance 5 Hours | #REF! | 5 Hours
VIC | AusNet | 2025-05-02 07:00 | 2025-05-07 18:00 | South Morang - Sydenham No.2 500 kV Line | This is a high impact outage only if the Forecast Operational Demand in Victoria region is greater than 7,000 MW A credible contingency event during this planned outage could: • Cause a large reduction in generation in Victoria • Restrict power transfer across the Victoria - South Australia interconnector (Heywood interconnector). | Day: 120 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 5.5 Days | #REF! | 5.5 Days
VIC | AusNet | 2025-05-07 07:00 | 2025-05-07 17:00 | Dederang - Wodonga 330 kV Line | This line outage offloads X5 220 kV line. Possible load shedding and risk of large reduction in generation in NSW and interconnector capacity between NSW - Victoria following a credible contingency | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-05-08 07:00 | 2025-05-08 17:00 | Dederang - Wodonga 330 kV Line | This line outage offloads X5 220 kV line. Possible load shedding and risk of large reduction in generation in NSW and interconnector capacity between NSW - Victoria following a credible contingency | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-05-13 07:00 | 2025-05-13 17:00 | Moorabool–Sydenham No.2 500 kV Line | <<NEW since the last notification>> A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 4 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-05-20 07:00 | 2025-05-20 17:00 | Ballarat - Waubra 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-05-20 07:00 | 2025-05-20 17:00 | Bendigo - Kerang 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-05-21 07:00 | 2025-05-21 17:00 | Ballarat - Waubra 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-05-21 07:00 | 2025-05-21 17:00 | Ballarat - Waubra 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-05-21 07:00 | 2025-05-21 17:00 | Ballarat - Waubra 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-05-21 07:00 | 2025-05-21 17:00 | Ballarat - Waubra 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-05-22 07:00 | 2025-05-22 15:00 | Ballarat - Waubra 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 8 Hours | #REF! | 8 Hours
VIC | AusNet | 2025-05-22 07:00 | 2025-05-22 15:00 | Ballarat - Waubra 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 8 Hours | #REF! | 8 Hours
QLD | Powerlink | 2025-05-27 08:00 | 2025-05-30 11:59 | Strathmore - Ross (8857) 275 kV Line | This is a high impact outage because the recall time is greater than 30 minutes. A credible contingency event during this planned outage may require market intervention through issuing of directions. | Day: 24 hrs-Night: 18 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | QLD Commissioning 3.2 Days | #REF! | 3.2 Days
QLD | Powerlink | 2025-05-30 12:00 | 2025-05-30 14:00 | Strathmore - Ross (8857) 275 kV Line | This is a high impact outage because the recall time is greater than 30 minutes. A credible contingency event during this planned outage may require market intervention through issuing of directions. | Day: 18 hrs-Night: 48 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | QLD Commissioning 2 Hours | #REF! | 2 Hours
VIC | AusNet | 2025-06-10 07:00 | 2025-06-10 17:00 | Kiamal SF-Red Cliffs 220 kV LINE | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-06-10 07:00 | 2025-06-10 17:00 | Kiamal SF-Red Cliffs 220 kV LINE | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-06-10 07:00 | 2025-06-10 17:00 | Red Cliffs-Wemen 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-06-11 07:00 | 2025-06-11 17:00 | Red Cliffs-Wemen 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 2 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | TOA | 2025-06-19 07:00 | 2025-06-19 12:00 | Ararat - Waubra 220 kV Line | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 1.5 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | T |  |  |  |  | VIC Maintenance 5 Hours | #REF! | 5 Hours
VIC | AusNet | 2025-06-20 07:00 | 2025-06-20 17:00 | Kiamal SF-Red Cliffs 220 kV LINE | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-06-21 07:00 | 2025-06-21 17:00 | Kiamal SF-Red Cliffs 220 kV LINE | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-06-22 07:00 | 2025-06-22 17:00 | Buronga - Redcliffs (OX1) 220 kV Line. | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | NSW / VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-06-23 07:00 | 2025-06-23 17:00 | Buronga - Redcliffs (OX1) 220 kV Line. | A credible contingency event during this planned outage may require: • Load shedding in the Victorian outer grid • Market intervention through issuing of directions. | Day: 60 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | NSW / VIC Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-06-23 07:00 | 2025-06-23 19:00 | Moorabool - Mortlake 500 kV Line | <<This outage has been WITHDRAWN!>> A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 2 hrs-Night: NA | Withdrawn | Withdrawn | [5 empty] | VIC / SA Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2025-06-24 07:00 | 2025-06-29 17:00 | South Morang - Sydenham No.1 500 kV Line | This is a high impact outage only if the Forecast Operational Demand in Victoria region is greater than 7,000 MW A credible contingency event during this planned outage could: • Cause a large reduction in generation in Victoria • Restrict power transfer across the Victoria - South Australia interconnector (Heywood interconnector). | Day: 120 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 5.4 Days | #REF! | 5.4 Days
VIC | AusNet | 2025-06-24 07:00 | 2025-06-24 19:00 | Moorabool - Mortlake 500 kV Line | <<This outage has been WITHDRAWN!>> A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 2 hrs-Night: NA | Withdrawn | Withdrawn | [5 empty] | VIC / SA Maintenance 12 Hours | #REF! | 12 Hours
SA | ElectraNet | 2025-06-30 07:30 | 2025-07-06 17:30 | Tailem Bend - South East No.1 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
VIC | AusNet | 2025-07-01 07:00 | 2025-07-01 17:00 | Moorabool - Mortlake 500 kV Line | <<This outage has been WITHDRAWN!>> A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 2 hrs-Night: NA | Withdrawn | Withdrawn | [5 empty] | VIC / SA Maintenance 10 Hours | #REF! | 10 Hours
VIC | AusNet | 2025-07-04 07:00 | 2025-07-04 17:00 | Moorabool - Mortlake 500 kV Line | <<This outage has been WITHDRAWN!>> A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 2 hrs-Night: NA | Withdrawn | Withdrawn | [5 empty] | VIC / SA Maintenance 10 Hours | #REF! | 10 Hours
SA | ElectraNet | 2025-07-07 07:30 | 2025-07-13 17:30 | Tailem Bend - South East No.2 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2025-07-14 07:30 | 2025-07-20 19:30 | Heywood - South East No.1 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT |  |  |  |  | T | VIC / SA Maintenance 6.5 Days | #REF! | 6.5 Days
VIC | AusNet | 2025-07-15 07:00 | 2025-07-20 17:00 | Moorabool–Sydenham No.1 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 120 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 5.4 Days | #REF! | 5.4 Days
SA | ElectraNet | 2025-07-21 07:30 | 2025-07-27 17:30 | Heywood - South East No.2 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT |  |  |  |  | T | VIC / SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2025-07-28 07:30 | 2025-08-03 17:30 | Tailem Bend - Tungkillo No.1 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2025-08-04 07:30 | 2025-08-10 17:30 | Tailem Bend - Tungkillo No.2 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
VIC | AusNet | 2025-08-08 07:00 | 2025-08-13 17:00 | South Morang - Sydenham No.2 500 kV Line | This is a high impact outage only if the Forecast Operational Demand in Victoria region is greater than 7,000 MW A credible contingency event during this planned outage could: • Cause a large reduction in generation in Victoria • Restrict power transfer across the Victoria - South Australia interconnector (Heywood interconnector). | Day: 120 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 5.4 Days | #REF! | 5.4 Days
QLD | Powerlink | 2025-08-19 08:00 | 2025-11-24 07:59 | Nebo - Strathmore (822) 275 kV Line | This is a high impact outage because the recall time is greater than 30 minutes. A credible contingency event during this planned outage may require market intervention through issuing of directions. | Day: 0 mins-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | QLD Maintenance 97 Days | #REF! | 97 Days
VIC | AusNet | 2025-08-26 07:00 | 2025-08-26 19:00 | Moorabool - Mortlake 500 kV Line | <<This outage has been WITHDRAWN!>> A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 2 hrs-Night: NA | Withdrawn | Withdrawn | [5 empty] | VIC / SA Maintenance 12 Hours | #REF! | 12 Hours
VIC | AusNet | 2025-09-01 07:00 | 2025-09-06 17:00 | Moorabool–Sydenham No.2 500 kV Line | A credible contingency event during this planned outage may require market intervention through issuing of directions | Day: 120 hrs-Night: NA | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | VIC Maintenance 5.4 Days | #REF! | 5.4 Days
QLD | Powerlink | 2025-11-03 07:00 | 2025-11-07 15:00 | Nebo - Broadsound (8846) 275 kV Line | This is a high impact outage because the recall time is greater than 30 minutes. A credible contingency event during this planned outage may require market intervention through issuing of directions. | Day: 8 hrs-Night: 8 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | QLD Commissioning 4.3 Days | #REF! | 4.3 Days
QLD | Powerlink | 2025-11-24 08:00 | 2025-11-28 17:00 | Nebo - Strathmore (822) 275 kV Line | This is a high impact outage because the recall time is greater than 30 minutes. A credible contingency event during this planned outage may require market intervention through issuing of directions. | Day: 48 hrs-Night: 48 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | QLD Maintenance 4.4 Days | #REF! | 4.4 Days
SA | ElectraNet | 2026-06-29 07:30 | 2026-07-05 17:30 | Tailem Bend - South East No.1 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2026-07-06 07:30 | 2026-07-12 17:30 | Tailem Bend - South East No.2 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2026-07-13 07:30 | 2026-07-19 19:30 | Heywood - South East No.1 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT |  |  |  |  | T | VIC / SA Maintenance 6.5 Days | #REF! | 6.5 Days
SA | ElectraNet | 2026-07-20 07:30 | 2026-07-26 17:30 | Heywood - South East No.2 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT |  |  |  |  | T | VIC / SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2026-07-27 07:30 | 2026-08-02 17:30 | Tailem Bend - Tungkillo No.1 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2026-08-03 07:30 | 2026-08-09 17:30 | Tailem Bend - Tungkillo No.2 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2027-06-28 07:30 | 2027-07-04 17:30 | Tailem Bend - South East No.1 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2027-07-05 07:30 | 2027-07-11 17:30 | Tailem Bend - South East No.2 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2027-07-12 07:30 | 2027-07-18 19:30 | Heywood - South East No.1 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT |  |  |  |  | T | VIC / SA Maintenance 6.5 Days | #REF! | 6.5 Days
SA | ElectraNet | 2027-07-19 07:30 | 2027-07-25 17:30 | Heywood - South East No.2 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT |  |  |  |  | T | VIC / SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2027-07-26 07:30 | 2027-08-01 17:30 | Tailem Bend - Tungkillo No.1 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2027-08-02 07:30 | 2027-08-08 17:30 | Tailem Bend - Tungkillo No.2 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2028-06-26 07:30 | 2028-07-02 17:30 | Tailem Bend - South East No.1 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2028-07-03 07:30 | 2028-07-09 17:30 | Tailem Bend - South East No.2 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2028-07-10 07:30 | 2028-07-16 19:30 | Heywood - South East No.1 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT |  |  |  |  | T | VIC / SA Maintenance 6.5 Days | #REF! | 6.5 Days
SA | ElectraNet | 2028-07-17 07:30 | 2028-07-23 17:30 | Heywood - South East No.2 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT |  |  |  |  | T | VIC / SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2028-07-24 07:30 | 2028-07-30 17:30 | Tailem Bend - Tungkillo No.1 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2028-07-31 07:30 | 2028-08-06 17:30 | Tailem Bend - Tungkillo No.2 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2029-07-02 07:30 | 2029-07-08 17:30 | Tailem Bend - South East No.1 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2029-07-09 07:30 | 2029-07-15 17:30 | Tailem Bend - South East No.2 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2029-07-16 07:30 | 2029-07-22 19:30 | Heywood - South East No.1 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT |  |  |  |  | T | VIC / SA Maintenance 6.5 Days | #REF! | 6.5 Days
SA | ElectraNet | 2029-07-23 07:30 | 2029-07-29 17:30 | Heywood - South East No.2 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT |  |  |  |  | T | VIC / SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2029-07-30 07:30 | 2029-08-05 17:30 | Tailem Bend - Tungkillo No.1 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2029-08-06 07:30 | 2029-08-12 17:30 | Tailem Bend - Tungkillo No.2 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2030-07-01 07:30 | 2030-07-07 17:30 | Tailem Bend - South East No.1 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2030-07-08 07:30 | 2030-07-14 17:30 | Tailem Bend - South East No.2 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2030-07-15 07:30 | 2030-07-21 19:30 | Heywood - South East No.1 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT |  |  |  |  | T | VIC / SA Maintenance 6.5 Days | #REF! | 6.5 Days
SA | ElectraNet | 2030-07-22 07:30 | 2030-07-28 17:30 | Heywood - South East No.2 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT |  |  |  |  | T | VIC / SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2030-07-29 07:30 | 2030-08-04 17:30 | Tailem Bend - Tungkillo No.1 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
SA | ElectraNet | 2030-08-05 07:30 | 2030-08-11 17:30 | Tailem Bend - Tungkillo No.2 275 kV Line | A credible contingency event during this planned outage could cause synchronous separation of the South Australia region from the rest of the NEM. During this planned outage: • Power transfer will be restricted across the Victoria - South Australia interconnector (Heywood interconnector). • Post contingent FCAS will be sourced within SA following Separation event. | Day: 6 hrs-Night: 12 hrs | Planned - SUBMIT | Planned - SUBMIT | [5 empty] | SA Maintenance 6.4 Days | #REF! | 6.4 Days
Withdrawn / UTP since the last notification